## Sheet1
|  | Start Date | End Date | Timeline
| FPGA Keyboard Piano | 2018-10-10 | 2018-12-07
| Proposal | 2018-10-10 | 2018-10-19
| Revised Proposal | 2018-10-19 | 2018-10-26
| Base Piano Design | 2018-10-26 | 2018-12-07
| Ocatave Switches | 2018-11-15 | 2018-12-07
| Piano Graphic | 2018-11-19 | 2018-12-07
| Real Time Graphic | 2018-11-23 | 2018-12-07
| Sustain Switch | 2018-11-26 | 2018-12-07
| Song Buttons | 2018-12-06 | 2018-12-07
If you want to edit this, please copy the sheet, which will give you edit access. First, make sure you are signed in to your Google account. Then, on the sheet, click File > Make a Copy. Now, after you save it your own Drive, you should be able to modify it.
Updated Gantt Chart Template: allowing for single-day events to show up, and including a white bar to indicate the current day during a given task (the "Active" color was changed to orange to make the current day more visible).
| Start Date | End Date | Timeline
FPGA Keyboard Piano | 2018-10-10 | 2018-12-07 | First day -------------------------------------------Last Day
Proposal | 2018-10-10 | 2018-10-19
Revised Proposal | 2018-10-19 | 2018-10-26
Base Piano Design | 2018-10-26 | 2018-12-07
Ocatave Switches | 2018-11-15 | 2018-12-07
Piano Graphic | 2018-11-19 | 2018-12-07
Real Time Graphic | 2018-11-23 | 2018-12-07
Sustain Switch | 2018-11-26 | 2018-12-07
Song Buttons | 2018-12-06 | 2018-12-07
| Start Date | End Date | Timeline
FPGA Keyboard Piano | 2018-10-10 | 2018-12-07
Proposal | 2018-10-10 | 2018-10-19
Revised Proposal | 2018-10-19 | 2018-10-26
Base Piano Design | 2018-10-26 | 2018-12-07
Ocatave Switches | 2018-11-15 | 2018-12-07
Piano Graphic | 2018-11-19 | 2018-12-07
Real Time Graphic | 2018-11-23 | 2018-12-07
Sustain Switch | 2018-11-26 | 2018-12-07
Song Buttons | 2018-12-06 | 2018-12-07
|  | Start Date | End Date | Gantt Chart
| FPGA Keyboard Piano | 2018-10-10 | 2018-12-07 | 10-10-2018-------------------------------------------12-07-2018
| Proposal | 2018-10-10 | 2018-10-19
| Revised Proposal | 2018-10-19 | 2018-10-26
| Base Piano Design | 2018-10-26 | 2018-12-07
| Ocatave Switches | 2018-11-15 | 2018-12-07
| Piano Graphic | 2018-11-19 | 2018-12-07
| Real Time Graphic | 2018-11-23 | 2018-12-07
| Sustain Switch | 2018-11-26 | 2018-12-07
| Song Buttons | 2018-12-06 | 2018-12-07
| Project Demo | ------------------- | 2018-12-07